## Slide 1: World of Warcraft: Pocket Buddy Project Plan
by Leon Oelen
DIN17SP

## Slide 2: CONTENTS
Summary
Overall approach – development phases
Deliverables
Technical requirements
Timetable

## Slide 3: Summary
World of Warcraft-themed application
Goal to put an endless number of resources into one place
Natively compiled mobile application developed using Flutter
Usage of public APIs and a database

## Slide 4: Overall approach – Requirements phase
Requirements phase
  Finding out what is required in terms of UI and functionality
  Learning the basics of the Flutter framework
  Researching possible APIs to integrate
  Researching clean development standards for mobile applications

## Slide 5: Overall approach – design phase
Design phase
  Mock-ups of the application
  Database layout
  Consistency between pages
  Looking at similar applications for inspiration

## Slide 6: Overall approach – implementation phase
Implementation phase
  Development using tools such as Visual Studio Code, Android Studio and GitHub
  Developed using the Dart programming language and numerous external libraries
  Agile development despite the project being a solo project
  Keeping up with the schedule

## Slide 7: Overall Approach – Testing Phase
Testing phase
  Making sure the latest build on GitHub is complete and functional
  Making sure that each functionality is tested
  Code cleanups
  Removal of “dead code”

## Slide 8: Deliverables
Project plan
Project report
Project worktime sheet
Full codebase on GitHub

## Slide 9: Technical Requirements
Mobile phone running either the Android or iOS operating system. Better performance on newer versions of each
Virtual emulator of a mobile device running either of the operating systems mentioned above

## Slide 10: Timetable
Week | Objectives
1 | Basics of the Flutter framework
2 | Skeleton development
3 | Adding resources to each class
4 | Planning out the functional aspects
5 | API integration
6 | Database development
7 | Code cleanup and testing
8 | Finalizing the application