## Sheet1
Worktime MOBILE APP PROJECT |  |  |  | https://github.com/leono93/world-of-warcraft-pocket-buddy
Date | Start time | End time | Time worked | Description of activities
2020-10-07 | 13 | 14 | 1 | Flutter Crash Course
2020-10-08 | 12 | 13 | 1 | Flutter setup + Project Plan
2020-10-09 |  |  | 0 | None // Worked on R&D course | 2 | Total hours needed: | 200
2020-10-12 | 8 | 16 | 8 | Flutter.dev introduction, playing with assets, buttons, containers, stacks |  | Total time worked: | 73
2020-10-13 | 10 | 16 | 6 | Routing, styling, creating and invoking existing classes based on each World of Warcraft class |  | HOURS LEFT OF TOTAL: | 127
2020-10-14 | 10 | 16 | 6 | Creating + implementing splash screen, creating higher resolution icons + bordering them, class titles with proper font
2020-10-15 | 10 | 16 | 6 | Looking into noSQL options for this app and fending off error after error trying to implement them. Implemented basis of Hive
2020-10-16 | 10 | 14 | 4 | Reading Blizzard API documentation and public resources on it as well as NodeJS implementation and libraries | 30
2020-10-19 | 11 | 16 | 5 | Implementing Blizzard.js library before making my own API endpoints. Requests to Blizzard API work after fixing outdated endpoints
2020-10-20 | 11 | 15 | 4 | Looking into the Flutter http package and testing example http calls to dummy JSON data
2020-10-21 | 11 | 12 | 1 | Fixed broken build and worked on R&D course
2020-10-22 | 11 | 15 | 4 | Fetching and mapping example JSON data. Also fixing endpoints for item + character retrieval from Blizzard API
2020-10-23 | 10 | 13 | 3 | Testing new token fetching and updating, planning out what and how to display from character info on frontend | 17
2020-10-26 | 9 | 15 | 6 | Adding resource redirects to each respective class, styling for ListViews when character list is implemented
2020-10-27 | 10 | 15 | 5 | Added info button + pages to each class with respective descriptions. Changed text styling, added assets for each spec.
2020-10-28 | 9 | 13 | 4 | Spent a few hours playing with Hive but decided not to use it and reverted the changes (lack of documentation, many deprecations)
2020-10-29 | 11 | 13 | 2 | Looked into SQLFlite options, minor style changes.
2020-10-30 | 8 | 11 | 3 | Planned out content management more // had job interview on this day | 20
2020-11-02 | 9 | 13 | 4 | Planning out Raider.io API integration
2020-11-03 |  |  | 0
2020-11-04 |  |  | 0
2020-11-05 |  |  | 0
2020-11-06 |  |  | 0 |  | 4
2020-11-09 |  |  | 0
2020-11-10 |  |  | 0
2020-11-11 |  |  | 0
2020-11-12 |  |  | 0
2020-11-13 |  |  | 0 |  | 0
2020-11-16 |  |  | 0
2020-11-17 |  |  | 0
2020-11-18 |  |  | 0
2020-11-19 |  |  | 0
2020-11-20 |  |  | 0 |  | 0